## Testcases
|  |  |  | Date | 2022-11-17
|  |  |  | Team ID | PNT2022TMID16274
|  |  |  | Project Name | Project - Car Resale Value Prediction
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
HomePage_TC_001 | UI | Home Page | Verify all the UI elements in Home page rendered properly |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not | - | All the UI elements rendered properly | Working as expected | Pass |  | N |  | Gowtham S
HomePage_TC_002 | Functional | Home Page | Verifiy the Data Entry page can be reachable. |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button. | - | User should navigate to Data Entry Page | Working as expected | Pass |  | N |  | Revanth Reddy B
DataEntryPage_TC_001 | UI | Data Entry Page | Verify all the UI elements in Data Entry page rendered properly |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not | - | All the UI elements rendered properly | Working as expected | Pass |  | N |  | Gowtham S
DataEntryPage_TC_002 | Functional | Data Entry Page | Verify user is able to enter all values |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered | Maruti Suzuki Swift, Maruti, 2019, 3000, Petrol | User should be able to enter all values in data entry page | Working as expected | Pass |  | N |  | Naveen M
DataEntryPage_TC_003 | Functional | Data Entry Page | Verifiy the Output Display page can be reachable. |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered 6. Press the submit Button | - | User should navigate to Output Display Page | Working as expected | Pass |  | N |  | Naveen M
OutputDisplayPage_TC_001 | UI | Output Display Page | Verify all the UI elements in Output Display page rendered properly |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered 6. Press the submit Button 7. Verify all the UI elements displayed or not | - | All the UI elements rendered properly | Working as expected | Pass |  | N |  | Selvaganapathy A
OutputDisplayPage_TC_002 | Functional | Output Display Page | Verify user is able to get predicted result |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered 6. Press the submit Button 7. Verify all the UI elements displayed or not 8. Verify if the predicted value is displayed or not | - | Predited Car Resale Value is displayed on the page | Working as expected | Pass |  | N |  | Revanth Reddy B

## Testscearnios
Test Scenarios
1 | Verify user is able to see home page?
2 | Verify user is able to navigate to data entry page?
3 | Verify user is able to see data entry page?
4 | Verify user is able to enter values in the fields?
5 | Verify user is able to navigate to output display page?
6 | Verify user is able to view the output display page?
7 | Veriify user is able to view the car resale value output in the output display page?